## Cover
BRAND LLC (limited liability company): 90 day launch plan (weeks 1 to 22)
Built October 8, 2026. Weeks follow the critical path in BUILD_BRIEF.md. Every model number comes from build/figures.json (Medium case, copper duty, FX 1,430 KRW per USD).
Tabs | Gantt: one row per task with ID, Task, Owner, Support, Start week, End week, Depends on, Cost, Cost type, Gate or deliverable, Basis, Status, then the week grid 1 to 22 shaded by conditional formatting from the Start and End columns. Costs: SUMIFS by owner, by cost type, by week and by owner and week, with a check against the model. Gate: the Day 90 criteria with the Medium model values beside each threshold and an input column for the actuals.
How to use | Lucy and Mark update the Status column (dropdown) and the Current week cell on the Gantt tab every Monday. Change Start or End weeks when a task slips; the grid, the Costs tab and the Dependency check recalculate. Edit the Depends on column as plain text (task IDs separated by a comma and a space, up to four); the check reads it. At week 22 fill the yellow Actual cells on the Gate tab; the result formula reads PASS, REVIEW or KILL.
Dependency check | Column O on the Gantt tab flags a task (1 per problem, 0 = ok) when a task it depends on starts after it starts, ends after it ends, or has an ID that is not in the list. Tasks may overlap their predecessors (for example the bank application starts while the document pack is finished). The helper columns to the right of the week grid (Dep 1 to Dep 4 and their flags) parse the Depends on text; they are formulas and need no editing.
Weeks and months | Month 1 is the first month with inventory live on Amazon (assumed early 2027). Weeks 1 to 9 are pre launch (Month 0), Month 1 is weeks 10 to 13, Month 2 is weeks 14 to 17, Month 3 is weeks 18 to 22. The Day 90 gate is the end of Month 3, week 22. No calendar dates are assigned. The weeks match the brief's critical path: broker and binding ruling in week 1, test inventory landed by week 8, listings weeks 6 to 9, validation weeks 10 to 22.
Owners | Lucy (owner, decides and pays), Mark (US operations support under a consulting agreement, prepares), attorney (US licensed), broker (customs broker), factory (COMQ supplier in China), 3PL (third party logistics warehouse in the US), VA (virtual assistant). The Korean tax accountant (세무사) and the US CPA (certified public accountant) appear in the Support column.
Cost column | USD cash out in the week range of the task. Launch budget tasks sum to the model's one time launch cost of $9,500 (evidence based total, management estimate split). Inventory rows are the Medium case purchase orders for Months 0 to 3 from the model's Cash Flow and Working Capital tab. Advertising is not a task cost: it sits in the P&L as a percent of revenue.
Legend | Yellow fill with blue text = input. Black = formula or fixed text. Green = reads another tab. Grid colors by owner: Lucy, Mark, attorney, broker, factory, 3PL, VA (see the swatches below). A Done task shows a green grid. Amber rows are gate milestones.
Basis | Evidence based = brief section 1, the August model, a verified regulatory fact or a model output. Management estimate = a cost or duration not yet quoted; the deliverable text names the placeholder to fill.
Rule | No hyphens or dashes in any text. Official form and registration numbers keep their format (Form SS-4, 599-64-00496).
Owner swatches
Lucy
Mark
attorney
broker
factory
3PL
VA
Done
Gate milestone
Headline numbers (Medium)
Opening capital | $39,000
Cash out in this plan, weeks 1 to 22 (Costs tab) | 58305.33
Funding gap in the model | $116K needed by Month 2 (1.2 times the peak need of $96K in Month 12)
Cash at end of Month 3 | ($9,084) before funding; $106,499 after funding
Day 90 gate, model result | PASS (Low REVIEW, High PASS)
Glossary (every acronym used in this workbook)
Glossary 1 of 7 | 3PL: third party logistics warehouse. ACOS: advertising cost of sales (ad spend divided by ad attributed sales). AOC: active optical cable. ASIN: Amazon Standard Identification Number. ASP: average selling price.
Glossary 2 of 7 | ATC: HDMI Authorized Test Center. CBP: US Customs and Border Protection. CL3: in wall cable fire rating (Class 3). COGS: cost of goods sold. CPA: US certified public accountant.
Glossary 3 of 7 | DDP: delivered duty paid. EIN: Employer Identification Number. FBA: Fulfillment by Amazon. FCC: Federal Communications Commission. FNSKU: Fulfillment Network Stock Keeping Unit (Amazon's barcode).
Glossary 4 of 7 | FOB: free on board (the price at the factory's port). FX: foreign exchange rate (KRW per USD). HDMI: High Definition Multimedia Interface. HTS: Harmonized Tariff Schedule. IP: intellectual property.
Glossary 5 of 7 | IRS: Internal Revenue Service. KPI: key performance indicator. LLC: limited liability company. ODI: overseas direct investment report (해외직접투자 신고). PO: purchase order.
Glossary 6 of 7 | PPC: pay per click advertising. Prop 65: California Proposition 65 warning label. QC: quality control. QR: quick response code. SKU: stock keeping unit.
Glossary 7 of 7 | SSN: Social Security Number. TACOS: total advertising cost of sales (ad spend divided by total sales). USPTO: United States Patent and Trademark Office. VA: virtual assistant. 세무사: Korean licensed tax accountant.

## Gantt
Gantt: 90 day launch plan, weeks 1 to 22 (Day 90 gate at week 22)
Grid shading is conditional formatting from Start week and End week, colored by Owner. Change Start, End, Depends on, Status or the Current week; nothing else needs editing. Acronyms are defined at first use and in the Cover glossary.
Current week |  | 1 | Opening capital | 39000 |  | Total cost | 58305.33 | Tasks | 45 | Dependency errors (0 = ok) |  | 0 | Done | 0
[15 empty] | Week | [8 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Gate | Helper columns: dependency IDs parsed from Depends on (formulas, no editing). Flag = that task starts after this one starts, ends after this one ends, or its ID is unknown.
ID | Task | Owner | Support | Start week | End week | Depends on | Cost | Cost type | Gate or deliverable | Basis | Status | Weeks | Cost per week | Dependency check | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | Dep 1 | Dep 2 | Dep 3 | Dep 4 | Flag 1 | Flag 2 | Flag 3 | Flag 4
Weeks 1 to 4: brand, entity, Korea filing, bank, customs (brief critical path items 1 to 5)
A1 | Decide the US brand name so the legal name BRAND LLC is final before any filing | Lucy | Mark | 1 | 1 |  | 0 | No cash cost | Name recorded in 11_Decision_Log.md; the same spelling is then used at the state, the IRS, the bank and Amazon | Evidence based | Not started | 1 | 0 | 0 | [26 empty] | 0 | 0 | 0 | 0
A2 | Trademark clearance search and USPTO (United States Patent and Trademark Office) application in one class through a US licensed attorney | attorney | Lucy | 1 | 2 | A1 | 1200 | Launch budget | USPTO serial number [PLACEHOLDER: serial number]. USPTO fee $350 per class (brief); attorney fee $850 is a management estimate [PLACEHOLDER: attorney quote] | Management estimate | Not started | 2 | 600 | 0 | [22 empty] | A1 |  |  |  | 0 | 0 | 0 | 0
A3 | Wyoming single member LLC: articles of organization, registered agent, operating agreement naming Lucy as 100% owner | attorney | Lucy | 1 | 2 | A1 | 700 | Launch budget | Certificate of organization. State fee $100 (brief); registered agent and operating agreement $600 are management estimates | Management estimate | Not started | 2 | 350 | 0 | [22 empty] | A1 |  |  |  | 0 | 0 | 0 | 0
A4 | EIN (Employer Identification Number) by phone or fax with Form SS-4; no SSN (Social Security Number) needed | attorney | Lucy | 2 | 2 | A3 | 0 | No cash cost | IRS (Internal Revenue Service) EIN confirmation letter [PLACEHOLDER: EIN]. The EIN is the importer of record number and the tax ID for the bank and Amazon | Evidence based | Not started | 1 | 0 | 0 | [22 empty] | A3 |  |  |  | 0 | 0 | 0 | 0
A5 | Written consulting or commission agreement between BRAND LLC and Mark Taylor (no equity, no authority to negotiate or sign) | attorney | Lucy, Mark | 2 | 3 | A3 | 500 | Launch budget | Signed agreement. Keeps the treaty position: no dependent agent in the US. Fee is a management estimate [PLACEHOLDER: attorney quote] | Management estimate | Not started | 2 | 250 | 0 | [22 empty] | A3 |  |  |  | 0 | 0 | 0 | 0
A6 | Document pack with the exact legal name: certificate, EIN letter, operating agreement, owner ID, US mailing address | Lucy | Mark | 2 | 3 | A4 | 250 | Launch budget | One folder used for the bank, Amazon and the broker. Notary, mailbox and courier costs are a management estimate | Management estimate | Not started | 2 | 125 | 0 | [22 empty] | A4 |  |  |  | 0 | 0 | 0 | 0
A7 | Korean overseas direct investment (ODI) report at the foreign exchange bank, before any capital moves | Lucy | Korean tax accountant (세무사) | 1 | 2 | A3 | 300 | Launch budget | Bank acceptance of the ODI report. Hard stop: no transfer before acceptance. 세무사 support fee is a management estimate [PLACEHOLDER: 세무사 quote] | Management estimate | Not started | 2 | 150 | 0 | [22 empty] | A3 |  |  |  | 0 | 0 | 0 | 0
A8 | USD bank account for BRAND LLC (Mercury or Relay; Payoneer or WorldFirst as fallback) | Lucy | Mark | 2 | 3 | A4, A6 | 0 | No cash cost | Account open under the exact legal name and EIN | Evidence based | Not started | 2 | 0 | 0 | [22 empty] | A4 | A6 |  |  | 0 | 0 | 0 | 0
A9 | Capital transfer of the opening capital $39,000 (KRW to USD at the FX input), then the Korean remittance and securities acquisition reports | Lucy | Korean tax accountant (세무사) | 3 | 3 | A7, A8 | 0 | No cash cost | Funds in the LLC account; bank acknowledgments of the follow up reports. Opening capital is the August funding ask (DECISIONS.md decision 3) | Evidence based | Not started | 1 | 0 | 0 | [22 empty] | A7 | A8 |  |  | 0 | 0 | 0 | 0
A10 | US CPA engaged: treaty memo (no permanent establishment from FBA stock), Form 5472 calendar, California nexus question | Lucy | Mark | 3 | 4 | A4 | 0 | No cash cost | Engagement letter and memo. Annual Form 5472 preparation $800 sits in the model from Year 2; penalty for a missed filing $25,000 | Management estimate | Not started | 2 | 0 | 0 | [22 empty] | A4 |  |  |  | 0 | 0 | 0 | 0
B1 | Customs broker engaged: power of attorney, importer of record set up on the EIN | broker | Mark | 1 | 1 |  | 150 | Launch budget | Signed broker agreement. Setup fee is a management estimate [PLACEHOLDER: broker quote] | Management estimate | Not started | 1 | 150 | 0 | [26 empty] | 0 | 0 | 0 | 0
B2 | Continuous customs bond ($500 per year) | broker | Lucy | 2 | 2 | A4, B1 | 500 | Launch budget | Bond number [PLACEHOLDER: bond number]. Required for formal entry; de minimis is gone | Evidence based | Not started | 1 | 500 | 0 | [22 empty] | A4 | B1 |  |  | 0 | 0 | 0 | 0
B3 | CBP (US Customs and Border Protection) binding ruling request filed in week 1: optical fiber cable 8544.70.00 versus electric conductor 8544.42.90 | broker | Mark, factory | 1 | 1 | B1 | 800 | Launch budget | Ruling request number [PLACEHOLDER: request number]. Preparation fee is a management estimate. Answer takes 30 to 90 days | Management estimate | Not started | 1 | 800 | 0 | [22 empty] | B1 |  |  |  | 0 | 0 | 0 | 0
B4 | Ruling answer window (30 to 90 days): track, answer CBP questions, keep the copper rate (40.1%) in every budget until the letter arrives | broker | Mark | 2 | 14 | B3 | 0 | No cash cost | Ruling letter [PLACEHOLDER: ruling number]. A fiber ruling moves landed COGS from 38.0% to 33.5% (Levers tab, lever 1) | Evidence based | Not started | 13 | 0 | 0 | [22 empty] | B3 |  |  |  | 0 | 0 | 0 | 0
Weeks 2 to 9: Amazon account, product compliance, test inventory, logistics (critical path items 6 and 7)
C1 | Amazon Professional seller account: identity verification, tax interview as a foreign owned entity, bank link | Lucy | Mark | 3 | 4 | A6, A8 | 0 | No cash cost | Seller Central account active. The $39.99 monthly fee is counted from Month 1 in task F2 | Evidence based | Not started | 2 | 0 | 0 | [22 empty] | A6 | A8 |  |  | 0 | 0 | 0 | 0
C2 | Amazon Brand Registry with the pending trademark application | Mark | Lucy | 4 | 4 | A2, C1 | 0 | No cash cost | Brand Registry approval: unlocks A+ content, Brand Store, video ads and hijacker protection | Evidence based | Not started | 1 | 0 | 0 | [22 empty] | A2 | C1 |  |  | 0 | 0 | 0 | 0
C3 | Product liability insurance quote ($1,000,000 cover, required once sales pass $10,000 in a month) and binder deposit | Mark | Lucy | 4 | 5 | A8 | 300 | Launch budget | Quote on file [PLACEHOLDER: insurer quote]. Deposit is a management estimate inside the launch budget | Management estimate | Not started | 2 | 150 | 0 | [22 empty] | A8 |  |  |  | 0 | 0 | 0 | 0
D1 | Factory document pack: HDMI (High Definition Multimedia Interface) Adopter certificate and ATC (HDMI Authorized Test Center) test report, FCC (Federal Communications Commission) test report for the active heads, CL3 (in wall cable fire rating, Class 3) documentation | factory | Lucy | 2 | 4 |  | 0 | No cash cost | Hard stop before the purchase order. [PLACEHOLDER: HDMI Adopter certificate number], [PLACEHOLDER: FCC report number], [PLACEHOLDER: CL3 report] | Evidence based | Not started | 3 | 0 | 0 | [26 empty] | 0 | 0 | 0 | 0
D2 | Packaging artwork: Ultra High Speed HDMI Cable category name (no version numbers), Prop 65 label, SOURCE and DISPLAY end markings, QR (quick response) code to the setup video, BRAND placeholder | Lucy | factory, Mark | 3 | 5 | A1, D1 | 400 | Launch budget | Approved artwork proof. Artwork fee is a management estimate | Management estimate | Not started | 3 | 133.3333 | 0 | [22 empty] | A1 | D1 |  |  | 0 | 0 | 0 | 0
D3 | Samples of the 5 launch SKUs shipped to Memphis for photography, direction proof test and packaging check | factory | Mark | 3 | 4 |  | 500 | Launch budget | Samples received and tested. Sample and courier cost is a management estimate | Management estimate | Not started | 2 | 250 | 0 | [26 empty] | 0 | 0 | 0 | 0
D4 | Lot 1 purchase order: 5 launch SKUs, about 1,067 units (about 213 per SKU, inside the brief's 100 to 300). FOB $7,871: 30% deposit at order, 70% at shipment | Lucy | factory | 4 | 7 | A9, D1, D2 | 7871.25 | Inventory | Signed PO and payment receipts. Units and FOB are the Medium Month 1 arrivals from the model (Cash Flow and Working Capital tab) | Evidence based | Not started | 4 | 1967.8125 | 0 | [22 empty] | A9 | D1 | D2 |  | 0 | 0 | 0 | 0
D5 | 3PL onboarding: account, receiving rules, FBA prep profile, Amazon shipping plan template | 3PL | Mark | 5 | 6 | C1 | 400 | Launch budget | 3PL agreement [PLACEHOLDER: 3PL quote]. Setup fee is a management estimate | Management estimate | Not started | 2 | 200 | 0 | [22 empty] | C1 |  |  |  | 0 | 0 | 0 | 0
D6 | Third party QC (quality control) inspection before departure and FNSKU (Fulfillment Network Stock Keeping Unit, Amazon's barcode) labels applied at the factory ($0.25 per unit in the landed cost) | factory | Lucy | 7 | 7 | D4 | 0 | No cash cost | QC report [PLACEHOLDER: inspection report]. Per unit cost is inside the lot 1 arrival charges (D7) | Evidence based | Not started | 1 | 0 | 0 | [22 empty] | D4 |  |  |  | 0 | 0 | 0 | 0
D7 | Lot 1 air DDP (delivered duty paid) shipment, formal entry by the broker, duty at the copper rate, 3PL receiving and FBA inbound prep: $9,153 on arrival | broker | factory, 3PL | 8 | 8 | B2, D5, D6 | 9152.75 | Inventory | Entry summary and 3PL receiving report. Freight, duty, broker, inbound and QC per unit from the model (landed cost less FOB). Test inventory lands in week 8 (brief critical path item 7) | Evidence based | Not started | 1 | 9152.75 | 0 | [22 empty] | B2 | D5 | D6 |  | 0 | 0 | 0 | 0
D8 | First FBA inbound shipment from the 3PL; stock checked in before Month 1 | 3PL | Mark | 8 | 9 | D7 | 0 | No cash cost | FBA inventory available in Seller Central | Evidence based | Not started | 2 | 0 | 0 | [22 empty] | D7 |  |  |  | 0 | 0 | 0 | 0
Weeks 5 to 9: listings and content (critical path item 8)
E1 | Photography and video for the 7 image slots and the video slot (09_Amazon_Listing_Kit.docx image brief) | Mark | VA | 5 | 7 | D3 | 2300 | Launch budget | Final images and video files. Studio cost is a management estimate [PLACEHOLDER: studio quote] | Management estimate | Not started | 3 | 766.6667 | 0 | [22 empty] | D3 |  |  |  | 0 | 0 | 0 | 0
E2 | Listing copy: one parent ASIN per line with children by length, titles under 200 characters, five bullets, backend keywords, HDMI naming rule | VA | Mark | 6 | 7 | C2 | 500 | Launch budget | Listing flat file uploaded. VA hours are a management estimate | Management estimate | Not started | 2 | 250 | 0 | [22 empty] | C2 |  |  |  | 0 | 0 | 0 | 0
E3 | A+ content (7 modules) and Brand Store | VA | Mark | 7 | 9 | C2, E1, E2 | 300 | Launch budget | A+ pages approved by Amazon. VA hours are a management estimate | Management estimate | Not started | 3 | 100 | 0 | [22 empty] | C2 | E1 | E2 |  | 0 | 0 | 0 | 0
E4 | Keyword research, PPC (pay per click advertising) campaign structure (auto plus manual), negative keyword list, ad budget caps | Mark | VA | 8 | 9 | E2 | 150 | Launch budget | Campaigns built and paused until stock is live. Keyword tool subscription is a management estimate | Management estimate | Not started | 2 | 75 | 0 | [22 empty] | E2 |  |  |  | 0 | 0 | 0 | 0
E5 | Spec Match finder page and trade up registration form (off Amazon email list), QR setup video live | Mark | VA | 8 | 10 | E1 | 250 | Launch budget | Pages live and linked from the insert card. Site tool cost is a management estimate | Management estimate | Not started | 3 | 83.3333 | 0 | [22 empty] | E1 |  |  |  | 0 | 0 | 0 | 0
E6 | Listings live with the price ladder (list price versus sale price) and launch coupon; PPC campaigns switched on | Mark | Lucy | 9 | 10 | D8, E3, E4 | 0 | No cash cost | Month 1 starts (first month with inventory live on Amazon) | Evidence based | Not started | 2 | 0 | 0 | [22 empty] | D8 | E3 | E4 |  | 0 | 0 | 0 | 0
Weeks 10 to 22: 90 day validation, Months 1 to 3 (critical path item 9)
F1 | Month 1 selling: Medium plan 150 units, revenue $6,300; Vine enrollment and insert card for review velocity; daily listing and account health check | Mark | Lucy, VA | 10 | 13 | E6 | 0 | No cash cost | Weekly KPI sheet: conversion, TACOS, return rate, contribution per SKU. Advertising is in the P&L at 30% of revenue, not in this cost column | Evidence based | Not started | 4 | 0 | 0 | [22 empty] | E6 |  |  |  | 0 | 0 | 0 | 0
F2 | Fixed costs Months 1 to 3: software, insurance and misc $850 per month plus the Professional seller fee $39.99 per month | Lucy |  | 10 | 22 | C1 | 2669.97 | Fixed cost | Paid monthly from the LLC account. August model fixed cost lines | Evidence based | Not started | 13 | 205.3823 | 0 | [22 empty] | C1 |  |  |  | 0 | 0 | 0 | 0
F3 | Lot 2 purchase order in Month 1 (arrives Month 2): about 582 units, FOB $4,292 (30% deposit, 70% at shipment) | Lucy | factory | 10 | 12 | D4, E6 | 4292.29 | Inventory | PO and payment receipts, placed once listings are live (E6). Order up to level from the reorder table (05_Operating_Processes.docx section 5) | Evidence based | Not started | 3 | 1430.7633 | 0 | [22 empty] | D4 | E6 |  |  | 0 | 0 | 0 | 0
F4 | Lot 2 arrival: air freight, duty, broker, inbound and QC $4,991 | broker | factory, 3PL | 14 | 14 | F3 | 4991.11 | Inventory | Entry summary and 3PL receiving report | Evidence based | Not started | 1 | 4991.11 | 0 | [22 empty] | F3 |  |  |  | 0 | 0 | 0 | 0
F5 | Month 2 selling: Medium plan 240 units, revenue $10,080; first keyword pruning and negative keyword pass; coupon review | Mark | VA | 14 | 17 | F1 | 0 | No cash cost | Weekly KPI sheet; TACOS must be falling month over month by the gate | Evidence based | Not started | 4 | 0 | 0 | [22 empty] | F1 |  |  |  | 0 | 0 | 0 | 0
F6 | Lot 3 purchase order in Month 2 (arrives Month 3): about 743 units, FOB $5,485 | Lucy | factory | 14 | 16 | F3, F4 | 5485.28 | Inventory | PO and payment receipts, placed once lot 2 has arrived (F4) and the Month 1 sales are known | Evidence based | Not started | 3 | 1828.4267 | 0 | [22 empty] | F3 | F4 |  |  | 0 | 0 | 0 | 0
F7 | Funding line in place by Month 2: the model draws $116K (1.2 times the peak need of $96K in Month 12) so the cash balance never goes negative | Lucy | Mark | 12 | 17 | A9, A10 | 0 | No cash cost | Signed line of credit or investor agreement [PLACEHOLDER: lender or investor]. Korean change report before the money moves. Amount from the Funding and Breakeven tab (Medium) | Evidence based | Not started | 6 | 0 | 0 | [22 empty] | A9 | A10 |  |  | 0 | 0 | 0 | 0
F8 | Lot 3 arrival: air freight, duty, broker, inbound and QC $6,378 | broker | factory, 3PL | 18 | 18 | F6 | 6378.32 | Inventory | Entry summary and 3PL receiving report | Evidence based | Not started | 1 | 6378.32 | 0 | [22 empty] | F6 |  |  |  | 0 | 0 | 0 | 0
F9 | Month 3 selling: Medium plan 360 units, revenue $15,120; hold ad caps; collect the gate evidence | Mark | VA | 18 | 22 | F5 | 0 | No cash cost | Weekly KPI sheet and the Gate tab filled in with actuals | Evidence based | Not started | 5 | 0 | 0 | [22 empty] | F5 |  |  |  | 0 | 0 | 0 | 0
F10 | Lot 4 purchase order in Month 3 (arrives Month 4, after the gate): about 917 units, FOB $6,764; sized down if the gate reads REVIEW or KILL | Lucy | factory | 18 | 21 | F6, F8 | 6764.36 | Inventory | PO and payment receipts, placed once lot 3 has arrived (F8). Arrival charges fall in Month 4, outside this plan | Evidence based | Not started | 4 | 1691.09 | 0 | [22 empty] | F6 | F8 |  |  | 0 | 0 | 0 | 0
F11 | Bind the $1,000,000 product liability policy ($1,200 per year) before Month 2, when Medium monthly sales pass $10,000 | Mark | Lucy | 12 | 13 | C3 | 1200 | Insurance | Policy certificate [PLACEHOLDER: policy number]. Premium is the model input (management estimate) | Management estimate | Not started | 2 | 600 | 0 | [22 empty] | C3 |  |  |  | 0 | 0 | 0 | 0
F12 | Weekly operating cadence: Monday KPI review (Mark prepares, Lucy decides), inventory position, account health, returns log | Mark | Lucy | 10 | 22 | F1 | 0 | No cash cost | 13 weekly notes in the shared folder (05_Operating_Processes.docx section 7) | Evidence based | Not started | 13 | 0 | 0 | [22 empty] | F1 |  |  |  | 0 | 0 | 0 | 0
Week 22: Day 90 gate (critical path items 9 and 10)
G1 | Day 90 gate pack: actuals for every criterion on the Gate tab, cash runway after funding the next PO, listing and IP status | Mark | VA | 21 | 22 | F9, F12 | 0 | No cash cost | GATE: Gate tab result PASS, REVIEW or KILL. Medium model result at Day 90: PASS | Evidence based | Not started | 2 | 0 | 0 | [22 empty] | F9 | F12 |  |  | 0 | 0 | 0 | 0
G2 | Gate decision by Lucy: PASS scales winners on ocean freight and delists losers; REVIEW fixes and retests within 30 days; KILL stops further capital and moves to Plan B | Lucy | Mark | 22 | 22 | G1 | 0 | No cash cost | GATE: signed decision note in 11_Decision_Log.md. Ocean PO is sized at the gate from the reorder table; not in this budget | Evidence based | Not started | 1 | 0 | 0 | [22 empty] | G1 |  |  |  | 0 | 0 | 0 | 0
Notes
Advertising (30% of revenue in Months 1 to 3, Medium) is paid from Amazon proceeds inside the P&L and is not a task cost here.
Inventory rows D4, D7, F3, F4, F6, F8 and F10 equal the model's inventory cash out for Months 0 to 3 ($44,935); the Costs tab checks this.
The ocean freight purchase order after a PASS is sized at the gate from the reorder table and is outside this budget (critical path item 10).
Korean follow up reports (remittance, securities acquisition, annual business performance) and the overseas financial account report are on 06_Compliance_Checklist.xlsx.

## Costs
Costs: cash out by owner, by cost type, by week and by owner and week (SUMIFS over the Gantt tab)
Every cell here is a live formula over the Gantt tab except the model reference values, which are written from build/figures.json (Medium case) for the check rows.
By owner | Tasks | Cost | Share
Lucy | 15 | 28033.15 | 48.08%
Mark | 12 | 4200 | 7.203%
attorney | 4 | 2400 | 4.116%
broker | 7 | 21972.18 | 37.68%
factory | 3 | 500 | 0.8576%
3PL | 2 | 400 | 0.686%
VA | 2 | 800 | 1.372%
Total | 45 | 58305.33 | 100%
Check: owner total less Gantt total (0 = ok) |  | 0
By cost type, with the model reference | Tasks | Cost | Model reference (Medium) | Check (0 = ok) | Reference source
Launch budget | 17 | 9500 | 9500 | 0 | One time launch costs, Month 1 (August model, evidence based)
Inventory | 7 | 44935.36 | 44935.359 | 0 | Inventory cash out Months 0 to 3, Cash Flow and Working Capital tab (lot FOB plus arrival charges)
Fixed cost | 1 | 2669.97 | 2669.97 | 0 | Fixed $850 plus seller fee $39.99 per month, Months 1 to 3
Insurance | 1 | 1200 | 1200 | 0 | Product liability premium per year, model input from Month 2
No cash cost | 19 | 0 | 0 | 0 | Tasks with no cash cost in the plan window
Total cash out, weeks 1 to 22 | 45 | 58305.33 | 58305.329 | 0
Opening capital (Gantt tab) |  | 39000
Plan cash out less opening capital (before Amazon proceeds) |  | 19305.33 |  |  | Amazon proceeds in Months 1 to 3 are not in this plan. The model's cash balance at the end of Month 3 is ($9,084) before funding and $106,499 after the $116K draw in Month 2.
By basis | Tasks | Cost | Share
Evidence based | 27 | 48105.33 | 82.51%
Management estimate | 18 | 10200 | 17.49%
By week: cost of every task spread evenly over its weeks (Cost per week column), SUMIFS on Start week and End week
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | Total
Cash out in the week | 2050 | 1975 | 758.3333 | 2501.1458 | 3217.8125 | 3184.4792 | 3084.4792 | 9411.0833 | 258.3333 | 1719.479 | 1636.1456 | 2236.1456 | 805.3823 | 7024.919 | 2033.809 | 2033.809 | 205.3823 | 8274.7923 | 1896.4723 | 1896.4723 | 1896.4723 | 205.3823 | 58305.33
Cumulative cash out | 2050 | 4025 | 4783.3333 | 7284.4792 | 10502.2917 | 13686.7708 | 16771.25 | 26182.3333 | 26440.6667 | 28160.1456 | 29796.2913 | 32032.4369 | 32837.8192 | 39862.7382 | 41896.5472 | 43930.3562 | 44135.7385 | 52410.5308 | 54307.0031 | 56203.4754 | 58099.9477 | 58305.33
Opening capital less cumulative cash out | 36950 | 34975 | 34216.6667 | 31715.5208 | 28497.7083 | 25313.2292 | 22228.75 | 12817.6667 | 12559.3333 | 10839.8544 | 9203.7087 | 6967.5631 | 6162.1808 | -862.7382 | -2896.5472 | -4930.3562 | -5135.7385 | -13410.5308 | -15307.0031 | -17203.4754 | -19099.9477 | -19305.33
Check: week total less Gantt total (0 = ok) | [22 empty] | 0
Month in the model | Pre | Pre | Pre | Pre | Pre | Pre | Pre | Pre | Pre | M1 | M1 | M1 | M1 | M2 | M2 | M2 | M2 | M3 | M3 | M3 | M3 | M3
By owner and week (SUMIFS on Owner, Start week and End week)
Owner | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | Total
Lucy | 150 | 275 | 258.3333 | 2101.1458 | 2101.1458 | 1967.8125 | 1967.8125 | 0 | 0 | 1636.1456 | 1636.1456 | 1636.1456 | 205.3823 | 2033.809 | 2033.809 | 2033.809 | 205.3823 | 1896.4723 | 1896.4723 | 1896.4723 | 1896.4723 | 205.3823 | 28033.15
Mark | 0 | 0 | 0 | 150 | 916.6667 | 766.6667 | 766.6667 | 158.3333 | 158.3333 | 83.3333 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
attorney | 950 | 1200 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400
broker | 950 | 500 | 0 | 0 | 0 | 0 | 0 | 9152.75 | 0 | 0 | 0 | 0 | 0 | 4991.11 | 0 | 0 | 0 | 6378.32 | 0 | 0 | 0 | 0 | 21972.18
factory | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
3PL | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
VA | 0 | 0 | 0 | 0 | 0 | 250 | 350 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
Total | 2050 | 1975 | 758.3333 | 2501.1458 | 3217.8125 | 3184.4792 | 3084.4792 | 9411.0833 | 258.3333 | 1719.479 | 1636.1456 | 2236.1456 | 805.3823 | 7024.919 | 2033.809 | 2033.809 | 205.3823 | 8274.7923 | 1896.4723 | 1896.4723 | 1896.4723 | 205.3823 | 58305.33
Check: owner and week total less Gantt total (0 = ok) | [22 empty] | 0
Open tasks by owner (Status not Done)
Lucy | 15
Mark | 12
attorney | 4
broker | 7
factory | 3
3PL | 2
VA | 2

## Gate
Gate: Day 90 criteria (end of Month 3, week 22) with the model values beside each threshold
Result rule: KILL if any kill trigger fires; PASS if every modeled pass threshold is met; REVIEW otherwise. REVIEW means fix and retest within 30 days. KILL means: No further capital, sell down inventory, delist losers, move to Plan B.
Model values are the Medium case from build/figures.json (Low and High shown for reference). Fill the yellow Actual cells at week 22; the Result column and the overall result are formulas.
# | Criterion | Pass threshold | Kill trigger | Pass value | Kill value | Test direction | Medium model (Month 3) | Low model | High model | Medium model result | Actual at Day 90 | Actual result | Source and basis
1 | Unit session conversion: number of the 5 launch SKUs at or above 8% | at or above 3 of 5 SKUs | none (see the hero row) | 3 | n/a | at or above | not modeled | not modeled | not modeled | n/a |  |  | Observed in Seller Central (Business Reports). Evidence based threshold
2 | Hero SKU (8K 10M) unit session conversion | at or above 8% | below 5% | 8% | 5% | at or above | not modeled | not modeled | not modeled | n/a |  |  | Observed in Seller Central. Evidence based threshold
3 | TACOS in Month 3 (ad spend divided by total revenue) | at or below 30% | above 40% | 30% | 40% | at or below | 30% | 37% | 26% | PASS |  |  | Model: Monthly PL Y1 Y2, Month 3 ad spend phase rate. Evidence based (August model)
4 | TACOS falling month over month: Month 2 actual (enter here) must be above the Month 3 actual in the row above | Month 3 below Month 2 | none | n/a | n/a | falling | flat (phase rate 30% in Months 1 to 3) | flat | flat | n/a |  |  | Observed from the advertising reports. The model holds one phase rate for Months 1 to 3, so this test applies to actuals only
5 | Return rate in Month 3 | at or below 4% | above 7% | 4% | 7% | at or below | 3% | 4% | 2.5% | PASS |  |  | Model: returns % assumption. Evidence based (August model)
6 | Contribution per unit before advertising on at least 3 of 5 SKUs (hero basis in the model) | at or above $11 | below $8 (hero) | 11 | 8 | at or above | 12.14 | 8.18 | 15.355 | PASS |  |  | Model: ASP less landed COGS, referral, FBA, returns, storage (Monthly PL Y1 Y2). Enter the hero actual
7 | Cash runway after funding the next purchase order, months | at or above 4 months | below 2 months | 4 | 2 | at or above | 10.202 | 15.2612 | 4.0398 | PASS |  |  | Model: cash after the funding draw divided by the Months 4 to 6 burn (Cash Flow and Working Capital). Before funding the Medium runway is 0.0 months
8 | Suppressed listing or intellectual property complaint: days the longest one has been open (0 = none) | none open | any open more than 14 days | 0 | 14 | at or below | not modeled | not modeled | not modeled | n/a |  |  | Observed in Account Health. Evidence based threshold
| Overall Day 90 result | [8 empty] | PASS | 8 | Enter every actual | Column L counts the empty Actual cells. Low model result REVIEW, High PASS.
| Month 3 model context (Medium, from build/figures.json) | Medium | Low | High
| Units sold in Month 3 | 360 | 216 | 558
| Revenue in Month 3 | 15120 | 8208 | 23994
| Net in Month 3 (after fixed costs and the seller fee) | -1055.59 | -2160.07 | 1439.66
| Cumulative net, Months 1 to 3 (includes the $9,500 launch costs) | -12514.97 | -14815.97 | -7314.445
| Contribution per unit after advertising, Month 3 | -0.46 | -5.88 | 4.175
| Cash balance at end of Month 3 before funding | -9084.329 | -611.7984 | -10531.6757
| Cash balance at end of Month 3 after funding | 106498.6975 | 135871.6482 | 30386.6273
| Funding gap in the model (1.2 times the peak cash need) | 115583.0265 | 136483.4466 | 40918.303
| Funding needed by month | Month 2 | Month 2 | Month 1
| Peak cash need and month | $96K in Month 12 | $114K in Month 24 | $34K in Month 7
| 18 month revenue and net (Amazon US) | $1.17M and $153K | $0.63M and ($20K) | $1.85M and $447K
| Cumulative breakeven month | Month 8 | none | Month 5
Reference: Month 12 gate (outside this 90 day plan; the same PASS, REVIEW, KILL rule)
# | Criterion | Pass threshold | Kill trigger | Pass value | Kill value | Test direction | Medium model (Month 12) | Low model | High model | Medium model result
1 | Monthly revenue in Month 12 | at or above $70,000 | below $50,000 | 70000 | 50000 | at or above | 86100 | 46740 | 136654 | PASS
2 | Cumulative net at Month 12 | at or above $0 | below ($25,000) | 0 | -25000 | at or above | 38040.12 | -27160.16 | 156979.355 | PASS
3 | TACOS in Month 12 | at or below 15% | above 25% | 15% | 25% | at or below | 15% | 22% | 11% | PASS
4 | Return rate in Month 12 | at or below 3% | above 5% | 3% | 5% | at or below | 3% | 4% | 2.5% | PASS
5 | Operating cash flow, lower of Months 11 and 12 | positive in Months 11 and 12 | negative Months 10 to 12 with a funding gap above $50,000 | 0 | gap above $50,000 | at or above | 7587.3433 | -2242.59 | 25226.0633 | PASS
| Overall Month 12 result | [8 empty] | PASS | Low KILL, High PASS
Glossary (the same list is on the Cover tab)
3PL: third party logistics warehouse. ACOS: advertising cost of sales (ad spend divided by ad attributed sales). AOC: active optical cable. ASIN: Amazon Standard Identification Number. ASP: average selling price.
ATC: HDMI Authorized Test Center. CBP: US Customs and Border Protection. CL3: in wall cable fire rating (Class 3). COGS: cost of goods sold. CPA: US certified public accountant.
DDP: delivered duty paid. EIN: Employer Identification Number. FBA: Fulfillment by Amazon. FCC: Federal Communications Commission. FNSKU: Fulfillment Network Stock Keeping Unit (Amazon's barcode).
FOB: free on board (the price at the factory's port). FX: foreign exchange rate (KRW per USD). HDMI: High Definition Multimedia Interface. HTS: Harmonized Tariff Schedule. IP: intellectual property.
IRS: Internal Revenue Service. KPI: key performance indicator. LLC: limited liability company. ODI: overseas direct investment report (해외직접투자 신고). PO: purchase order.
PPC: pay per click advertising. Prop 65: California Proposition 65 warning label. QC: quality control. QR: quick response code. SKU: stock keeping unit.
SSN: Social Security Number. TACOS: total advertising cost of sales (ad spend divided by total sales). USPTO: United States Patent and Trademark Office. VA: virtual assistant. 세무사: Korean licensed tax accountant.